## sunymappings
TOPIC | SUBTOPIC | Consideration For (Inputs) | Activity | Outcomes (see comment) | Milestone Indicator (Outputs) | Participants | Participant Group | Method | Exemplar@SUNY | Guiding documents
E.1. Data Governance—Strategic/Qualitative | E.1.1 Identification of goals and roles |  | Convene data governance group (strategic Level) | Institutional Data Governance goals identified and defined, Research Data goals are indentified and defined | Overarching goal statements | VPR, Campus Provost, CIO, Library Dean | Strategic Leaders | Create Data Governance Council |  | ["Data Governance Institute Guidance"¦ https://datagovernance.com/the-data-governance-basics/]
The policies, procedures, and processes pertaining to authority, control, | E.1.1 Identification of goals and roles |  | Convene data governance group (strategic Level) | Institutional Data Governance roles and responsibilities are identified and defined, Research Data Governance roles and responsibilities are identified and defined | RACI matrix, Data Curation Roles Planning Matrix | VPR, Campus Provost, CIO, Library Dean | Strategic Leaders | Task Force |  | ["Research Data Curation - EDUCASE Working Group Paper"¦https://library.educause.edu/-/media/files/library/2018/5/ewg1803pdf.pdf]
and shared decision-making (planning, monitoring, and enforcement) over the management of data assets
| E.1.2 Vision and/or policy |  | Convene data governance group (strategic Level) | Institution has a clearly defined vision for data management (including research data) | Vision statement | VPR, Campus Provost, CIO, Library Dean | Strategic Leaders | Create Data Governance Council | ["Stony Brook Data Governance Framework"¦https://www.stonybrook.edu/commcms/irpe/about/_files/DataGovFramework.pdf], ["Binghamton Data Governance Policy"¦https://www.binghamton.edu/operations/policies/policy-300.html]
| E.1.2 Vision and/or policy |  | Convene data governance group (strategic Level) | Institution has a clearly defined high-level policies for data management (including research data) | Data policies, Research data specific policies | VPR, Campus Provost, CIO, Library Dean | Strategic Leaders | Create Data Governance Council | ["Stony Brook Research Data Ownership Retention and Access Policy"¦https://www.stonybrook.edu/policy/_pdf/research_data_ownership_retention_and_access_policy.pdf]
| E.1.3 Data management organization |  | Build organizational infrastructure to support RDM | RDM organization to support data-related activities exists |  | VPR, Campus Provost, CIO, Library Dean | Strategic Leaders | Create Data Governance Council (strategic level) and Data Governance Working Group (tactical level)
| E.1.4 Organizational values, including DEI | E.1.1, E.1.2, E.1.5
| E.1.5 Data management value proposition |  | Convene data governance group | Institution has a clearly defined statement of purpose and value for all data including research data | Data Management Value Statement | VPR, Campus Provost, CIO, Library Dean | Strategic Leaders | Strategic planning
| E.1.6 Data needs assessment |  | Conduct data needs assessments | Data needs assessment completed at the desired level of analysis including: researcher, student, discipline, institution, unit, library | Data Needs Assessment reports | Librarians, Researchers, IT office, Students | Connectors/Facilitators | Needs assessments, stakeholder survey, investigate number of, size, publishing location of datasets, investigate existing grant funded projects and grants |  | ["ARL/CARL Joint Task Force on Research Data Services Final Report"¦ https://www.arl.org/wp-content/uploads/2021/07/2021.07.16-arl-carl-joint-task-force-on-research-data-services-final-report.pdf]
| E.1.7 Purpose and value of data | E.1.5, E.1.2 |  |  | Vision statement | VPR, Campus Provost, CIO, Library Dean | Strategic Leaders | Strategic planning
| E.1.8 Organization intent regarding FAIR data |  |  | Organizational intent regarding FAIR data is well defined across the institution and contributes to vision and policy | FAIR is integrated into research policies | Librarians, Researchers, IT office, Students | Connectors/Facilitators
| E.1.9 End-use support |  |  | Research data is prepared and processed for end use and resuse | Data usage statistics demonstrate data use and reuse | Librarians and researchers | SME and Implementers
| E.1.10 Stewardship | E.1.3
E.2 Data Governance—Legal and Regulatory Compliance | E.2.1 Privacy |  |  | Data governance legal policies, framework, and plans exist and are continually updated | Data policies, Research data specific policies
The policies, procedures, and processes to manage and monitor an organization’s regulatory [and] legal responsibilities and risks pertaining to data. | E.2.2 Ethics | E.1.3, E.2 |  | Research is conducted ethically |  | IRB | SME and Implementers
| E.2.3 Safety and security assurance | E.2
| E.2.4 Inventory |  | Conduct a dataset inventory | Dataset inventory exists and includes relevant dataset metadata including: repository, identifiers, data usage metrics, creators, funders, supporting grants | Dataset inventory | IT Head, Librarian | Connectors/Facilitators | Inventory
|  |  | Conduct a data services inventory | Data services inventory: includes relevant data services provided across institution or unit | Data Services inventory | IT Head, Librarian | Connectors/Facilitators | Inventory | Engage with Security Operations Center (SOC) Information Security Working Group, Enterprise Risk Management Committee | ["Research Data Curation - EDUCASE Working Group Paper"¦https://library.educause.edu/-/media/files/library/2018/5/ewg1803pdf.pdf], ["Research Data Services in US Higher Education - Ithaka S+R"¦https://sr.ithaka.org/publications/research-data-services-in-us-higher-education/]
| E.2.5 Risk assessment |  | Conduct a risk assessment | Risk is assessed and includes risks associated with unmanaged data, research subject privacy, data preservation, funder compliance | Risk Assessment | CISO, CIO, Chief Officer for Risk and Compliance | Connectors/Facilitators | Many Risk Assessment tools and framework (NISTIR 8062)
| E.2.6 Risk mitigation and management | E.2.5 | Implement solutions to mitigate and manage risk discovered in risk assessment | Risks determined in risk assessment are mitigated, managed, and controlled | Risk mitigation plan, Data Governance plans | CISO, CIO, Chief Officer for Risk and Compliance | Connectors/Facilitators | Many Risk Mitigation tools
| E.2.7 Sharing/licensing |  |  | Policies for sharing and licensing data exist | Data Use Agreement | Counsel | SME and Implementers
| E.2.8 Social license for use and reuse |  |  | Community standards for social licensing of and (re)use of data exist
| E.2.9 Jurisdiction for sharing and reuse | E.2.7 |  |  |  | Counsel | SME and Implementers
E.3 Data Culture and Reward Structure | E.3.1 Roles and responsibilities |  | Define roles and responsibilities for building a strong data sharing culture and rewards structure | Roles and responsibilities are identified and defined for a strong data sharing culture with rewards structure | RACI matrix, Data Curation Roles Planning Matrix | VPR, Campus Provost, Library Dean, HR, Department Chairs, Students, Faculty Senate | Strategic Leaders | Task Force
The collective beliefs and behaviors of the people in an organization concerning the value and management of research data. Practices designed to recognize the advantages and accomplishments of sharing data. | E.3.2 Recognition of data management |  | Build a data culture | Data management work is recognized and supported | Recognition for data management through awards, professional expectations, data metrics, promotion | VPR, Campus Provost, Library Dean, HR, Librarians, Researchers | Strategic Leaders | Task Force, Campus working groups |  | ["Helios Open"¦https://www.heliosopen.org/ourwork]
| E.3.3 Value of data workers |  | Build a data culture | Data workers are valued and data work is recognized and supported | Recognition for data sharing and open data through awards, professional expectations, data metrics, promotion | HR, Faculty, Administrators | Connectors/Facilitators | Data Governance Council
| E.3.4 Promotion and tenure |  | Build a data culture | Promotion and tenure reflect the importance of open research and scholarship | Data sharing is incentivized in promotion and tenure work through use of data metrics and open publishing, community engagement | VPR, Campus Provost, Library Dean, HR, Department Chairs, Students, Faculty Senate
| E.3.5 Integrity of research and data |  | Integrate integrity or research and data into curriculum and RDM training | Researchers are expected to follow standard practices to ensure research and outputs maintain integrity |  | Librarians, Researchers | SME and Implementers | Data Governance Council
| E.3.5 Integrity of research and data |  | Perform accuracy checks on all shared or published datasets, Create README files | Data is checked for accuracy before publishing and sharing |  | Librarians, Researchers | SME and Implementers
| E.3.6 FAIR data principles | P.5 |  | FAIR data principles are integrated into research data management work | RDM training includes FAIR | Librarians, Researchers | SME and Implementers |  |  | ["The FAIR Guiding Principles for scientific data management and stewardship"¦ https://www.nature.com/articles/sdata201618], ["FAIR Principles from Go-FAIR"¦ https://www.go-fair.org/fair-principles/]
| E.3.7 Maintenance of FAIR data | E.3.6, P.5 |  | Data sharing infrastructure supports FAIR data
| E.3.8 Incentives and impact for sharing and reuse |  |  | Appropriate incentives (or disincentives) exist for data sharing and reuse | Data usage metrics exist
| E.3.9 Disincentives for sharing and reuse | E.3.8
| E.3.10 CARE and ethics | E.2.9 |  | Principles for Indigenous Data Governance are respected (CARE, OCAP, and ethics) | Statement on Indigenous ethics of ownership | Librarians, Researchers | SME and Implementers |  |  | ["First Nation Principles of Ownership"¦https://fnigc.ca/ocap-training/], ["CARE Principles"¦ https://www.gida-global.org/care], ["DCN CARE Data Primer"¦ https://github.com/DataCurationNetwork/data-primers/blob/main/CARE%20Primer/care-primer.md]
E.4 Education and Workforce Development | E.4.1 Workforce skills inventory | E.2.4 | Conduct a Workforce skills inventory to determine an organization's internal capacity to conduct and support RDM | Internal workforce skills inventory exists to document strengths and weaknesses in workforce capacity to conduct RDM | Workforce skills inventory (internal) | Department Deans, Provost | Connectors/Facilitators | Skills inventory
Training to provide staff with the necessary skills and expertise for data-related activities and RDM. Includes leadership support and formal and informal training. |  |  | Conduct a Workforce skills inventory to determine needs for students to build workforce skills to conduct or support RDM | Statewide workforce skills inventory exists to document strengths and weaknesses in workforce capacity to conduct RDM across NYS are documented | Inventory of state workforce needs that can be addressed through education | System Admin | Strategic Leaders | Skills inventory
| E.4.2 Workforce preparedness in new and advanced technologies |  | Provide training and opportunities for employees to build their skills and expertise in emerging technologies | Institution can support RDM through Institutional workforce preparedness activities in new and advanced technologies | Suite of internal workforce training offered | Department Deans, Provost | Connectors/Facilitators | Training
|  |  | Build workforce preparedness programs for emerging technologies for state workforce | State Workforce is well prepared to adapt and innovate in response to emerging technologies | Educational programs equip students to work with data and emerging technologies | System Admin | Strategic Leaders | Training
| E.4.3 Data management training |  | Provide research data management training as a data service | RDM training is available for researchers, faculty, staff, and students | Asynchronous and synchronous RDM training | Librarians, IT, Research Administrators | SME and Implementers | Asynchronous web-based training, short courses, integrated training in education offerings
| E.4.4 HR’s supporting role in workforce development and training |  | Provide research data management training to data service providers | Continual opportunities for RDM training for staff supported | Organization funds training and employee time spent on training | HR, Librarians, IT, Research and Economic Development | SME and Implementers | Data curation, preservation, management training opportunities inform providers of RDM services
| E.4.5 Promotional paths and career development | E.3.3, E.3.4 |  |  |  |  | Connectors/Facilitators
E.5 Resources—Allocation and Sustainability | E.5.1 Sources of funding |  | Determine initial financial support models to launch RDM infrastructure | RDM is funded through dedicated financial resources (may be temporary) | Sources of funding discovered and captured | Finance, Research and Economic Development, VPR, Provost | Strategic Leaders | Apply for grants
The distribution and longevity of funding to attain and maintain robust research data programs and RDM infrastructure. | E.5.2 Long-term funding |  | Integrate RDM costs into sustainable financial models | RDM funding is operationalized with long-term funding | Long-term funding integrated into budget | Finance, Research and Economic Development, VPR, Provost | Strategic Leaders | Budget process
| E.5.3 Staffing |  | Increase existing staff skills in RDM, redeploy existing staff, or hire new staff members with RDM skills | Staffing is considered in resource allocation | Organization chart | HR, Finance, Research and Economic Development, VPR, Provost | Strategic Leaders | Training
E.6 Community Engagement | E.6.1 Stakeholder communities |  | Build Stakeholder communities of practice: local, campus, system, national, international | Active RDM stakeholder communities exist | Active communities of practice exist along continuum of emergent data community to established data community | Librarians, Researchers, Faculty, Administration | Connectors/Facilitators | Communities of Practice, Task Groups, Mentor models, GRANTED work | GRANTED, Data Curation Network, SUNY campus groups, SUNY system groups | ["Leveraging Data Communities to Advance Open Science - Ithaka S+R"¦https://sr.ithaka.org/publications/leveraging-data-communities-to-advance-open-science/]
Outreach and interactions among organizations or individuals with shared goals or interests concerning research data activities or RDM | E.6.2 Modes of communication |  | Establish communication channels | Consistent modes of communication are established |  | Librarians, Researchers, Faculty, Administration | Connectors/Facilitators
| E.6.3 Partners/partnerships |  | Map potential local stakeholders and partners | Relevant unit, departmental, institutional, SUNY system-wide, state, national, and funder partnerships are built and nurtured |  |  | Connectors/Facilitators Strategic Leaders
| E.6.4 Engagement across knowledge domains and sectors | E.6.1
| E.6.5 Inclusivity in interactions | E.6.1, E.1.4
| E.6.6 Data services and the beneficiaries | E.6.1, E.2.4 |  | Data services across the institution are offered, documented, and appropriate for researcher needs. |  | Librarians, Research Administrators | Connectors/Facilitators |  |  | ["ARL/CARL Joint Task Force on Research Data Services Final Report"¦ https://www.arl.org/wp-content/uploads/2021/07/2021.07.16-arl-carl-joint-task-force-on-research-data-services-final-report.pdf]
P.1 Chain of Control (Custody of Data) | P.1.1 Roles and responsibilities (Chain of Control) | P.1 |  | Ownership of data assets within research project is documented, controlled, and managed |  | Researcher, IT | SME and Implementers
A complete, fully documented step-by-step history of a data asset in an organization, i.e., who has possession of a data asset, at what time, and for what purpose, at all times throughout the lifecycle of the data asset. | P.1.2 Implementation authority | E.1.1, P.1
| P.1.3 Centralized inventory of services, groups, and resources |  | Conduct project-specific inventory | Project-specific inventory of services, groups, and resources exists |  | Researcher | SME and Implementers
| P.1.4 Provenance | P.1.1 |  |  |  | Researcher, Sponsored Programs Research Office | SME and Implementers
P.2 Financial Aspects of Planning | P.2.1 Funding models for provisioning resources (project) | P.2 | Estimate costs for research project and find suitable funding sources. | Project planning includes financial considerations to consider in estimating or assessing the costs associated with all research data and RDM activities over the data lifecycle |  | Researcher | SME and Implementers |  |  | ["Making Research Data Publicly Accessible: Estimates of Institutional & Researcher Expenses"¦https://doi.org/10.29242/report.radsexpense2024], ["Cost and Value of Data" ¦ https://www.ncbi.nlm.nih.gov/books/NBK562702/]
Factors to consider in estimating or assessing the costs associated with all research data and RDM activities over the data lifecycle. | P.2.2 Funding sources (project) | P.2 |  |  |  | Researcher | SME and Implementers
| P.2.3 Decision-making tools to assess costs (project) | P.2 |  |  |  | Researcher | SME and Implementers
| P.2.4 Cost-benefit analysis (project) | P.2 |  |  |  | Researcher | SME and Implementers |  |  | ["Cost and Value of Data" ¦ https://www.ncbi.nlm.nih.gov/books/NBK562702/]
| P.2.5 Cost breakdown by lifecycle stage (project) | P.2 |  |  |  | Researcher | SME and Implementers
| P.2.6 Downstream lifecycle costs (project) | P.2 |  |  |  | Researcher | SME and Implementers |  |  | ["Making Research Data Publicly Accessible: Estimates of Institutional & Researcher Expenses"¦https://doi.org/10.29242/report.radsexpense2024], ["COGR Survey Costs"¦ https://www.cogr.edu/results-cogr-survey-cost-complying-new-nih-dms-policy-1]
| P.2.7 Staffing and training | P.2
P.3 Data Management Planning | P.3.1 Written data management plans (DMPs) | E.4.3 |  | All required projects should have a Research Data Management and Sharing Plan to meet funder and institutional needs. |  | Researcher, Librarian, Sponsored Programs, Pre-award | SME and Implementers |  |  | ["DMPTool" ¦ https://dmptool.org/], ["SUNY Guidance on Research Data Management" ¦ https://sunyolis.libguides.com/c.php?g=1290338&p=9476771]
The process of organizing and specifying objectives and activities throughout the research data lifecycle. | P.3.2 Purpose/intent of research study and context of anticipated data use | E.4.3, P.3 |  |  |  | Researcher, Librarian, Sponsored Programs, Pre-award | SME and Implementers
| P.3.3 Specification of data objects, metadata, analysis tools, and workflows throughout the lifecycle | E.4.3, P.3 |  |  |  | Researcher, Librarian, Sponsored Programs, Pre-award | SME and Implementers
| P.3.4 Machine-readable DMPs | E.4.3, P.8 |  | Research data architecture could include machine-readable DMPs to automate and make actionable RDM process
| P.3.5 Linkage of DMPs to administrative records | P.8 |  | Research data architecture enables linkage of machine-readable DMPs other institutional data systems
| P.3.6 Data organization in, e.g., a database and a repository, to facilitate future access |  |  | Appropriate repository is determined to for data deposit to facilitate future access (institutional repository, shared repository, domain-specific or generalist) |  | IT, Library | Connectors/Facilitators |  |  | ["Registry of Research Data Repositories" ¦ https://www.re3data.org/]
| P.3.7 Data management expertise and training | E.4.3 |  | Research data project participants have necessary RDM expertise and access to RDM training
P.4 Data Objects | P.4.1 Quantitative and qualitative | P.4 |  | Data objects created or used as part of the research project are known |  | Researcher, Librarian, Sponsored Programs, Pre-award | SME and Implementers
An entity that, together with associated Representative Information (i.e., metadata), is produced or used in a research study | P.4.2 Measurements, including images, audio recordings, and photos/videos | P.4
| P.4.3 Observation | P.4
| P.4.4 Survey | P.4
| P.4.5 Software | P.4
| P.4.6 Model | P.4
| P.4.7 Documentation (text) |  |  | Data objects and their representation metadata should be documented to maintain accuracy, integrity, and reliability |  | Researcher | SME and Implementers
| P.4.8 Specimen (physical sample) | P.4
| P.4.9 Presentation | P.4
P.5 FAIR | P.5.1 Organizational support for making data more FAIR | E.3.6 |  | FAIR data is supported and implemented in research project design |  | Researcher | SME and Implementers |  |  | ["The FAIR Guiding Principles for scientific data management and stewardship"¦ https://www.nature.com/articles/sdata201618], ["FAIR Principles from Go-FAIR"¦ https://www.go-fair.org/fair-principles/]
Findability, Accessibility, Interoperability, Reuse: a set of guiding principles to support the reusability of data that are beneficial to all scholarly digital research objects. | P.5.2 Identification of methods/guidelines vis-à-vis FAIR principles | E.3.6
P.6 Data/Metadata Considerations | P.6.1 Criteria for selection of data/metadata | P.6 |  | Research projects utilize data and metadata practices following RDM guidelines
Factors to take into account prior to conducting a research study | P.6.2 Nature of data/metadata required | P.6
| P.6.3 Intended extent of FAIRness | P.5, P.6 |  | Appropriate metadata is assigned to data to ensure data is FAIR
| P.6.4 Methods to capture and store data/metadata | P.6
| P.6.5 Metadata schema | P.6 | Use standard metadata to ensure research data is FAIR
P.7 Data Architecture | P.7.1 Design | P.7 |  | Project data architecture should be designed to meet institutional and project data governance needs
The fundamental structure of an organization's research data management (RDM) system embodied in its components, their relationships to each other and to the environment, and the principles guiding its design and evolution. Includes, for example, the underlying storage technologies, networking, hardware, system interfaces, authentication mechanisms, data brokers, monitoring platforms, semantic interoperability tools, long-term preservation services, and HPC. | P.7.2 Processing operations | P.7
| P.7.3 Workflow | P.7
| P.7.4 Model | P.7
| P.7.5 LIMS | P.7
| P.7.6 Hosting and storage, cloud storage | P.7
| P.7.7 Configuration management | P.7
| P.7.8 Interoperability among different architectures | P.7
| P.7.9 Security | P.7 |  | Data architecture follows project and campus security requirements for access and use |  | IT, CIO | SME and Implementers
| P.7.10 Existing standards | P.7
P.8 Hardware and Software Infrastructure | P.8.1 Organizational research needs |  |  | Hardware and software infrastructure for projects producing data should match organizational research needs and standards |  | Researcher, IT | SME and Implementers
The physical and non-physical functional components that collectively form a foundation for conducting research and RDM | P.8.2 Tools to support data-related processes | P.8 |  | Project hardware and software infrastructure should support RDM
| P.8.3 Models that connect infrastructure to data processes and workflow | P.8 |  |  |  | Researcher, IT | SME and Implementers
| P.8.4 Interoperability | P.8
| P.8.5 Persistent instrument identifiers | P.8
| P.8.6 Sustainability of data vis-à-vis obsolete infrastructure | P.8
| P.8.7 Security and privacy considerations | P.8, P.12 |  |  |  | IT, IT security | SME and Implementers
| P.8.8 Staff expertise and support staff | P.8
P.9 Research Data Standards | P.9.1 Criteria, i.e., general vs. domain-specific standards |  |  | Projects should be developed using federal, organizational, and community research data standards |  | Researcher | SME and Implementers
Documents, including codes, specifications, recommended practices, classifications, test methods and guides, that describe how data should be stored or exchanged for the consistent collection and interoperability of that data across different systems, sources, and users. | P.9.2 Sources of standards/guidelines for data/metadata | P.9 |  |  |  | Researcher | SME and Implementers
| P.9.3 Quality standards | P.9 |  |  |  | Researcher | SME and Implementers
| P.9.4 Community-based standards/conventions | P.9 |  |  |  | Researcher | SME and Implementers
P.10 Assessment | P.10.1 Goals/definition of success |  | Establish project goals for research data | RDM goals for research projects and research data should be clearly articulated
Evaluation of the success of a research project against expectations set before the project has started | P.10.2 Metrics for tracking use and impact measures, including reuse |  | Create and use data metrics | Data metrics are used to track use and impact, Data metrics are aligned with project goals |  | Researcher | SME and Implementers |  |  | ["Make Data Count: Data usage"¦ https://makedatacount.org/data-usage/]
P.11 Communication and Outreach | P.11.1 Methods to share and reuse data/metadata | P.11 |  | For all research projects, communication and outreach methods and practices should be clearly defined |  | Researcher | SME and Implementers
Engagement and interactions among groups and Individual working in similar research areas | P.11.2 Allocation of credit to project team members |  | Assign credit to all project members | Research contributions are well defined and transparent |  | Researcher | SME and Implementers |  |  | ["CRediT Taxonomy Standard"¦https://credit.niso.org/ ]
| P.11.3 Promotion of data to communities of interest | P.11, E.6
| P.11.4 Cross-institution cooperation | P.11, E.6.1
| P.11.5 Requests for additional data from community | P.11
P.12 Access Control Associated with Data Sensitivity | P.12.1 Identification of responsible parties for access | E.2.6, P.1.1, P.12 | Use and follow appropriate data use agreements, Assign appropriate licenses to products of research | Data use agreements are followed, Research data governance frameworks are established and implemented |  | Researcher | SME and Implementers
Methods and requirements to limit the individuals and groups permitted to view or use protected data. | P.12.2 Ease of maintenance and implementation of records | P.1, P.12
| P.12.3 Regulatory compliance | E.2, P.12
| P.12.4 Sensitive data/PII | E.2.3, P.12
| P.12.5 Limited disclosure, e.g., IP | E.2.7, P.12
| P.12.6 Licensing for reuse | E.2.7, P.12
GA.1 Data Types | GA.1.1 Measurements, including images, audio recordings, photos/videos | GA.1 | Review Data Curation Network Primers for your dataset during the Generate/Acquire phase | Unique collection, generation, and storage challenges with specific data types generated in each research project are reviewed and mitigated |  | Researcher | SME and Implementers |  |  | ["Data Curation Primers by Type of Data"¦https://github.com/DataCurationNetwork/data-primers/tree/main ]
Classifications or categories of data, each with unique collection, generation, and storage challenges | GA.1.2 Text file | GA.1
| GA.1.3 Computation, simulation | GA.1
| GA.1.4 Source code | GA.1
| GA.1.5 Observation | GA.1
| GA.1.6 Survey | GA.1
| GA.1.7 Transaction | GA.1
| GA.1.8 Social media | GA.1
GA.2 Data Sources | GA.2.1 In-house generation by researchers | GA.2 |  | Considerations of specific data sources used in each research project are reviewed and documented. A ReadMe file or accompanying metadata exists to document project data generation and use. |  | Researcher | SME and Implementers
Where and from which processes data originates | GA.2.2 Remote generation by researchers | GA.2
| GA.2.3 In-field generation by researchers | GA.2
| GA.2.4 User facility generation by/for researcher | GA.2
| GA.2.5 Historical | GA.2
| GA.2.6 Human-annotated | GA.2
GA.3 Generated Experimental Data | GA.3.1 Source of objects/subjects | GA.3
Collection of information through active intervention by the researcher to induce and measure changes or to create differences when a variable is altered | GA.3.2 Characteristics of objects/subjects | GA.3
| GA.3.3 Conditions of research study | GA.3
| GA.3.4 Specification of instruments and tools | GA.3
| GA.3.5 Parameters for instruments and tools | GA.3
| GA.3.6 Methods, protocols, and calibration | GA.3
| GA.3.7 Data/metadata capture methods | GA.3
| GA.3.8 Provenance and capture methods | GA.3
| GA.3.9 Reproducibility | GA.3
GA.4 Generated Computational Data | GA.4.1 Input data/metadata | GA.4
Production of information resulting from executing a computer model or simulation | GA.4.2 Output data/metadata | GA.4
| GA.4.3 Hardware | GA.4
| GA.4.4 Parameters and conditions for computation | GA.4
| GA.4.5 Versioning | GA.4
| GA.4.6 Data/metadata capture methods | GA.4
| GA.4.7 Provenance and capture methods | GA.4
| GA.4.8 Verification/validation of output data | GA.4
GA.5 Qualitative Data | GA.5.1 Nature of objects/subjects | GA.5
Non-ordinal and focusing on qualities or characteristics | GA.5.2 Methods and protocols | GA.5
| GA.5.3 Metadata | GA.5
| GA.5.4 Paradata | GA.5
| GA.5.5 Data/metadata/paradata capture methods | GA.5
GA.6 Acquired Data | GA.6.1 From collaborators | GA.6
Obtained from a source outside of the researchers and which was not originally collected for the current research project | GA.6.2 From repositories | GA.6 |  | Persistent identifiers are recorded for reused datasets.
| GA.6.3 From the literature | GA.6 |  | All resources are appropriately referenced in research data outputs.
| GA.6.4 Aggregated datasets from multiple sources | GA.6 |  | Data use agreements follow requirements from sharing institution as well as researcher's institution
| GA.6.5 Provenance | GA.6 |  | Factors related to how data are acquired are reviewed and standardized |  | Researcher | SME and Implementers
| GA.6.6 Restrictions, fees, and usage agreements | GA.6
GA.7 Critically Evaluated (CE) Data | GA.7.1 Infrastructure to assure the greatest data integrity | GA.7 |  | Data should be collected and processed in a standardized way with rigorous methodology to serve as a standard |  | Researcher | SME and Implementers
Collected and processed in a standardized way with rigorous methodology to serve as a standard | GA.7.2 Single researcher dataset | GA.7
| GA.7.3 Aggregation of data evaluated by experts | GA.7
| GA.7.4 Reproducibility and uncertainty quantification | GA.7
| GA.7.5 Intellectual property rights | GA.7
GA.8 FAIR Principles | GA.8.1 Data born FAIR | P.5, GA.8 | Consider FAIR principles when generating data | FAIR data is supported and implemented during the Generate/Acquire phase |  | Researcher | SME and Implementers |  |  | ["The FAIR Guiding Principles for scientific data management and stewardship"¦ https://www.nature.com/articles/sdata201618], ["FAIR Principles from Go-FAIR"¦ https://www.go-fair.org/fair-principles/]
Compliance with a set of guiding principles proposed by a consortium of scientists and organizations to support the reusability of digital assets | GA.8.2 Data made FAIR | P.5, GA.8
| GA.8.3 FAIR digital objects | P.5, GA.8
| GA.8.4 FAIR on a continuous scale | P.5, GA.8
| GA.8.5 Guidelines/methodologies for each aspect: F, A, I, R | P.5, GA.8
| GA.8.6 Tools to capture FAIR provenance | P.5, GA.8
| GA.8.7 FAIR instruments and tools | P.5, GA.8
| GA.8.8 Not FAIR data (e.g., legacy data) | P.5, GA.8
GA.9 Community-Based Standards | GA.9.1 General vs. domain-specific | P.6 |  | Community-based standards for data and metadata are considered before data collection. Data should be well-defined and interoperable |  | Researcher | SME and Implementers
Technical specifications for encoding metadata for machine processing and exchange | GA.9.2 Standards development organizations vs. community consensus | P.6, GA.7
| GA.9.3 Data format and file structure | P.6, GA.7 | Use standardized file naming conventions and directory structure |  |  | Researcher | SME and Implementers |  |  | ["Cornell File Naming Tips"¦ https://data.research.cornell.edu/content/file-management], ["Build Your Directory Structure"¦ https://datamanagement.hms.harvard.edu/collect/directory-structure ]
| GA.9.4 Metadata format and file structure | P.6, GA.7
| GA.9.5 Vocabulary and ontology | P.6, GA.7
| GA.9.6 Interoperability | P.6, GA.7
GA.10 Acquisition Software | GA.10.1 Open source vs. proprietary | GA.10, P.8 |  | Factors related to acquisition software are reviewed and standardized before data generation or collection |  | Researcher | SME and Implementers
Programs that enable the collection and procurement of data | GA.10.2 LIMS | GA.10, P.8
| GA.10.3 Instrument control | GA.10, P.8
| GA.10.4 Electronic laboratory notebooks | GA.10, P.8 | Use Electronic Lab Notebooks to standardize documentation and processes in research
| GA.10.5 Audio and video recordings | GA.10, P.8
PA.1 Types of Processed Data | PA.1.1 Tables, spreadsheets | GA.1 | Review Data Curation Network Primers for your dataset during processing |  |  | Researcher | SME and Implementers |  |  | ["Data Curation Primers by Type of Data"¦https://github.com/DataCurationNetwork/data-primers/tree/main ]
Classifications or categories of data | PA.1.2 Charts, graphs | GA.1
| PA.1.3 Maps, vectors, images | GA.1
| PA.1.4 Instrument outputs | GA.1
| PA.1.5 Dynamic data | GA.1
| PA.1.6 Datasets from models and simulations | GA.1
| PA.1.7 Structured data, e.g., hierarchical organization | GA.1
PA.2 Preparation and Pre-Processing Methods | PA.2.1 Data cleaning | PA.2 | Follow best practices for data cleaning |  |  | Researcher | SME and Implementers |  |  | ["Data Cleaning: Detecting, Diagnosing, and Editing Data Abnormalities"¦https://doi.org/10.1371/journal.pmed.0020267 ]
Techniques by which raw data are transformed into complete datasets with consistent formatting such that data analysis can subsequently be performed. | PA.2.2 De-identification, anonymization | PA.2 | Follow best practices for de-identification |  |  | Researcher | SME and Implementers |  |  | ["Anonymization Techniques for Privacy Preserving Data Publishing: A Comprehensive Survey"¦https://ieeexplore.ieee.org/document/9298747 ]
| PA.2.3 Amputation and imputation | PA.2
| PA.2.4 Aggregation | PA.2
| PA.2.5 Validation and verification | PA.2
| PA.2.6 Curation | PA.2 | Review Data Curation Network Primers for your dataset during processing |  |  | Researcher | SME and Implementers |  |  | ["Data Curation Primers by Type of Data"¦https://github.com/DataCurationNetwork/data-primers/tree/main ]
| PA.2.7 Normalization of metadata | PA.2
PA.3 Analysis | PA.3.1 Manual | PA.3 | Determine what new data will be produced with data analysis and how to managed original raw data
| PA.3.2 Exploratory | PA.3
| PA.3.3 Descriptive | PA.3
| PA.3.4 Diagnostic | PA.3
| PA.3.5 Evaluative | PA.3
| PA.3.6 Predictive | PA.3
| PA.3.7 Prescriptive | PA.3
| PA.3.8 Correlational | PA.3
| PA.3.9 Statistical | PA.3
| PA.3.10 Automated, autonomous | PA.3
PA.4 Modeling | PA.4.1 Visualization | PA.4
| PA.4.2 ML, AI | PA.4
| PA.4.3 Iterative model fitting | PA.4
| PA.4.4 Integrated development environments, e.g., Jupyter, RStudio | PA.4
PA.5 Metadata | PA.5.1 Types of metadata | PA.5
"Data about data," i.e., data that define and describe the characteristics of other data [1] | PA.5.2 Responsible parties | PA.5
| PA.5.3 Specification of metadata standards | PA.5
| PA.5.4 Linked data structure | PA.5
| PA.5.5 Persistent identifiers (e.g., DOI, ORCID, ARK, ROR, PIDINST, Handles) |  | Use Persistent identifiers when possible (e.g., DOI, ORCID, ARK, ROR, PIDINST, Handles)
PA.6 Provenance | PA.6.1 Original authoritative copy | GA.6.5
Historical information on metadata, such as the origin, location, or source of the data, or on the ownership or location of an object or resource [1] | PA.6.2 Version identification | GA.6.5
| PA.6.3 Derivative product | GA.6.5
| PA.6.4 Aggregation | GA.6.5
| PA.6.5 Subset | GA.6.5
| PA.6.6 Timestamp | GA.6.5
| PA.6.7 CRediT taxonomy | P.11.2, GA.6.5
PA.7 Software | PA.7.1 Commercial vs custom | PA.7, P.8
A program used in performing an activity to produce a product or result [1] | PA.7.2 Open-source vs proprietary | PA.7, P.8
| PA.7.3 Aggregation tools | PA.7, P.8
| PA.7.4 Surveying tools | PA.7, P.8
| PA.7.5 Statistical tools | PA.7, P.8
| PA.7.6 Calculation and analysis tools | PA.7, P.8
| PA.7.7 APIs | PA.7, P.8
| PA.7.8 Database management tools | PA.7, P.8
| PA.7.9 Testing and validation tools | PA.7, P.8
| PA.7.10 Documentation | PA.7, P.8
| PA.7.11 Reproducibility and uncertainty quantification | PA.7, P.8
| PA.7.12 Versioning and maintenance | PA.7, P.8
| PA.7.13 Systems resilience and adaptability | PA.7, P.8
| PA.7.14 Source code repository | PA.7, P.8
| PA.7.15 Security and software updates | PA.7
| PA.7.16 Standards, protocols, and interfaces | PA.7, P.8
PA.8 Workflows and Middleware | PA.8.1 LIMS | PA.8 | Create and document research workflows
A set of chained operations, e.g., scripts that can involve several "ingredients" such as data, programs, models and other inputs, e.g., human and sensor observations; software that performs communication and input/output [1] | PA.8.2 Laboratory notebooks, e.g., electronic and paper | PA.8
| PA.8.3 Tools for automated metadata capture | PA.8
| PA.8.4 Anomaly detection and correction tools | PA.8
| PA.8.5 Collaboration tools | PA.8
| PA.8.6 Decisions regarding the need for additional data | PA.8
| PA.8.7 Process monitoring and evaluation | PA.8
| PA.8.8 Containerization | PA.8
| PA.8.9 Reusable workflow component | PA.8
| PA.8.10 Microservices | PA.8
| PA.8.11 Distributed workflow across sites | PA.8
| PA.8.12 Comprehensive report generation | PA.8
PA.9 Hardware | PA.9.1 Compute requirements | PA.9, P.8
Physical equipment used in the production of research data | PA.9.2 Storage requirements | PA.9, P.8
| PA.9.3 Network requirements | PA.9, P.8
| PA.9.4 Accelerator requirements | PA.9, P.8
SUR.1 Publishing | SUR.1.1 Repository, i.e., domain, generalist, institutional | SUR.1 | Determine how and where the research project will disseminate and publish results
Releasing research data, associated metadata, accompanying documentation, and software code (in cases where the raw data have been processed or manipulated) for re-use and analysis in such a manner that these data objects can be discovered on the Web and referred to in a unique and persistent way [1] | SUR.1.2 Data papers | SUR.1
| SUR.1.3 Software | SUR.1
| SUR.1.4 Updates to datasets and new software versions | SUR.1
| SUR.1.5 Data linking | SUR.1
| SUR.1.6 Persistent identifier | SUR.1
| SUR.1.7 Metadata | SUR.1
| SUR.1.8 Integrity of data | SUR.1
| SUR.1.9 Quality measures and assessment vis-à-vis fit for purpose | SUR.1
| SUR.1.10 Peer review of datasets and metadata | SUR.1
| SUR.1.11 Reference data/digital objects in journal articles | SUR.1
| SUR.1.12 Curation | SUR.1
| SUR.1.13 Publisher agreements and policies | SUR.1
| SUR.1.14 Incentives for data publishing | SUR.1, E.3.8
| SUR.1.15 Mitigation of disincentives for data publishing | SUR.1
SUR.2 Modes of Dissemination | SU2.1.1 Traditional journal article | SUR.2 | Consider where research project outputs will be published.
Methods and platforms for distributing data | SU2.1.2 Supplementary material | SUR.2
| SU2.1.3 On request | SUR.2
| SU2.1.4 Data landing page | SUR.2
| SU2.1.5 Workflow | SUR.2
| SU2.1.6 Mainstream media, e.g., newspapers, radio | SUR.2
| SU2.1.7 Social media, e.g., Twitter, Instagram | SUR.2
SUR.3 Attribution | SUR.3.1 Citation metrics | SUR.3 |  | All resources and data are cited appropriately as to the extend possible in published outputs |  | IT, Library, Researcher | SME and Implementers
Offers proper recognition to authors as well as permanent identification through the use of global persistent identifiers in place of URLs which can change frequently [1] | SUR.3.2 Citation impact | SUR.3
| SUR.3.3 Dataset citation | SUR.3 | Cite research datasets and share prefered dataset citation | Datasets can be and are cited in research outputs |  | Researcher | SME and Implementers |  |  | ["Make Data Count: Data usage"¦ https://makedatacount.org/data-usage/]
| SUR.3.4 Provenance | SUR.3
| SUR.3.5 Author identity management | SUR.3
| SUR.3.6 Use of persistent identifiers | SUR.3, PA.5
| SUR.3.7 Versioning | SUR.3
SUR.4 Modes of Sharing | SUR.4.1 Standardized formats | SUR.4 |  | When possible, data is shared in standard formats, in public repositories, and discoverable
Locations and forms in which data sharing occurs | SUR.4.2 Interoperability tools | SUR.4
| SUR.4.3 Discovery platform | SUR.4
| SUR.4.4 Catalog | SUR.4
| SUR.4.5 Registries of repositories | SUR.4 |  | Appropriate repository is determined to for data deposit to facilitate future access (institutional repository, shared repository, domain-specific or generalist) |  | IT, Library, Researcher | SME and Implementers |  |  | ["Registry of Research Data Repositories" ¦ https://www.re3data.org/]
SUR.5 Access | SUR.5.1 Internal access | SUR.5
The continued, available for use, ongoing usability of a digital resource | SUR.5.2 External access | SUR.5
| SUR.5.3 Programmatic access, i.e., API | SUR.5
| SUR.5.4 Virtual and physical enclaves | SUR.5
| SUR.5.5 Access vs visiting | SUR.5
| SUR.5.6 Availability statement | SUR.5
| SUR.5.7 Mitigation of barriers and economic constraints | SUR.5
SUR.6 Legal and Licenses | SUR.6.1 Ownership | SUR.6
Legal and regulatory issues as pertaining to research data | SUR.6.2 Encouragement and support for sharing, use, and reuse | SUR.6
| SUR.6.3 Indigeneous data rights | SUR.6
| SUR.6.4 Intellectual property rights/restrictions | SUR.6
| SUR.6.5 Usage agreements/terms/licenses and required permissions | SUR.6
| SUR.6.6 Data sharing agreements and licensing | SUR.6
| SUR.6.7 Service-level agreements | SUR.6
| SUR.6.8 Terms of service | SUR.6
| SUR.6.9 Standardized, machine-actionable license documents | SUR.6
| SUR.6.10 Citation requirements | SUR.6
SUR.7 Levels of Protection | SUR.7.1 Unclassified but sensitive information | SUR.7
Definitions of who has access to what data and based on what criteria | SUR.7.2 Security classification | SUR.7
| SUR.7.3 Protection of limited data/secure platforms/enclaves | SUR.7
| SUR.7.4 Constraints and restrictions on data use and sharing | SUR.7
| SUR.7.5 Anonymization | SUR.7
SUR.8 Architectures for Application, Use, and Reuse | SUR.8.1 Extensibility across communities, including machine-based interactions | SUR.8
| SUR.8.2 Capture of insights from ML and use of these to improve datasets for future AI applications | SUR.8
| SUR.8.3 Capture of data performance characteristics | SUR.8
| SUR.8.4 Location of data | SUR.8
| SUR.8.5 Migration strategies and mitigation against data loss | SUR.8
| SUR.8.6 Economic impact of reuse | SUR.8
PD.1 Criteria for Preservation | PD.1.1 Use | PD.1 | Consider relevant factors to appraise and select research data for curation and preservation |  |  | Librarians, Researchers | SME and Implementers |  |  | ["How to Appraise and Select Research Data fur Curation" ¦ https://www.dcc.ac.uk/guidance/how-guides/appraise-select-data]
Quantitative and qualitative metrics used to assess the need for long-term retention of data. | PD.1.2 Impact | PD.1
| PD.1.3 Value | PD.1
| PD.1.4 Uniqueness | PD.1
| PD.1.5 Cost | PD.1
| PD.1.6 Provenance | PD.1
| PD.1.7 Legal and regulatory | PD.1
PD.2 Sustainability | PD.2.1 Longevity and support | P.2
Longevity of the data infrastructure and data management systems | PD.2.2 Funding models | P.2
| PD.2.3 Business models | P.2
PD.3 Storage and Preservation | PD.3.1 Media to store and preserve data | PD.3
How data are stored, backed-up, and preserved | PD.3.2 File integrity | PD.3
| PD.3.3 Ability to do advanced searches | PD.3
| PD.3.4 Backup and recovery | PD.3
PD.4 Moving Data from One Service to Another across Organizations | PD.4.1 Roles and responsibilities | PD.4 | Assign roles and responsibilities for data when transfering between locations |  |  | IT, Library, Researcher | SME and Implementers
| PD.4.2 Registry maintenance and curation | PD.4
| PD.4.3 Disciplinary archives | PD.4
PD.5 Retention and Disposition Schedules | PD.5.1 Technical decisions, e.g., data archiving | PD.5 | Determine length of data retention at time of publication (10 years, permanent, etc.)
A plan of action that indicates the period of time to retain records | PD.5.2 Administrative/policy decisions | PD.5
| PD.5.3 Deaccessioning/end-of-life | PD.5
| PD.5.4 Legal documents | PD.5
| PD.5.5 End-of-life special considerations | PD.5
| PD.5.6 Recognition of removed data, i.e., tombstone page | PD.5